## Agile Project Plan
PROJECT NAME | SPRINT START DATE | SPRINT END DATE |  |  | PROJECT DELIVERABLE | In Sprint 2 of the condo management system, the development team will focus on delivering essential enhancements to improve user experience and system functionality. This includes implementing a secure registration system for users, an interactive dashboard for condo owners, a property profile management feature, a comprehensive financial management system, and a reservation system for common facilities. Accompanying these software features, the deliverables also encompass technical documentation, user manuals, detailed testing reports, a deployment guide, and training materials to ensure smooth adoption and operation. Performance metrics and a sprint review document will evaluate the success of these features, providing insights for future improvements. This suite of deliverables aims to meet user needs effectively while laying the groundwork for the system's continued development and scalability.
Urban Keys | February 8th | February 28th |  |  | SCOPE STATEMENT | The primary objective of Sprint 2 is to develop and enhance the condo management system by integrating secure registration processes for condo owners and rental users, implementing a comprehensive dashboard for condo owners, establishing a foundational property management framework, and setting up financial and reservation systems. This sprint aims to deliver critical functionalities that improve user experience, streamline property management tasks, and ensure transparent financial operations.
USER STORIES (#) | NAME | STORY POINTS (Fibonacci) | PRIORITY | DURATION (DAYS) | STATUS | COMMENTS
2 | Secure Registration for Condo Owners |  |  |  | Not started
2.1 | Registration Key Validation | 3 | High | 8 | Not started
2.2 | Condo Owner Account Creation | 5 | High | 10 | Not started
2.3 | Secure Authentication Setup | 3 | High | 8 | Not started
2.4 | User Feedback and Confirmation | 2 | Medium | 4 | Not Started
3 | Secure Registration for Rental Users |  |  |  | Not Started
3.1 | Registration Key Validation for Rental Users | 3 | High | 8 | Not Started
3.2 | Rental User Account Creation | 5 | High | 10 | Not Started
3.3 | Secure Authentication for Rental Users | 3 | High | 8 | Not Started
3.4 | User Feedback and Confirmation for Rental Users | 2 | Medium | 4 | Not Started
4 | Comprehensive Dashboard for Condo Owners |  |  |  | Not Started
4.1 | Design and implement the dashboard UI displaying property details. | 5 | High | 10 | Not Started
4.2 | Integrate financial details and status into the dashboard. | 8 | High | 16 | Not Started
4.3 | Ensure real-time data fetching for dashboard updates. | 5 | Medium | 10 | Not Started
5 | Creating a Property Profile |  |  |  | Not Started
5.1 | Develop a form for inputting property details by the property manager. | 3 | High | 6 | Not Started
5.2 | Implement the backend service for storing property profiles in MongoDB. | 5 | High | 10 | Not Started
6 | Uploading Condo Files |  |  |  | Not Started
6.1 | Create a file upload interface for condo managers. | 3 | Medium | 6 | Not Started
6.2 | Develop backend functionality for file storage and retrieval. | 5 | Medium | 10 | Not Started
7 | Detailed Information Entry |  |  |  | Not Started
7.1 | Design UI for entering unit, parking spot, and locker details. | 8 | High | 14 | Not Started
7.2 | Implement backend logic to link detailed info with specific properties. | 8 | High | 16 | Not Started
8 | Generation and Distribution of Registration Keys |  |  |  | Not Started
8.1 | Develop a system for generating unique registration keys. | 5 | High | 10 | Not Started
8.2 | Create a mechanism for sending keys to users via email. | 3 | High | 6 | Not Started
9 | Entering Condo Fee Information |  |  |  | Not Started
9.1 | Implement UI for entering condo fees per square foot and per parking spot. | 3 | High | 5 | Not Started
9.2 | Develop backend functionality to store and retrieve condo fee information. | 5 | High | 10 | Not Started
10 | Calculating and Presenting Unit Fees |  |  |  | Not Started
10.1 | Create a calculation module to determine fees based on condo and parking space sizes. | 8 | High | 18 | Not Started
10.2 | Design a feature in the property manager's dashboard for presenting calculated fees to condo owners. | 5 | High | 12 | Not Started
11 | Recording Operational Budget and Costs |  |  |  | Not Started
11.1 | Design input forms for recording operational budgets and costs. | 5 | Medium | 10 | Not Started
11.2 | Implement backend logic for aggregating and storing financial data. | 8 | Medium | 14 | Not Started
12 | Generating Annual Financial Reports |  |  |  | Not Started
12.1 | Develop a report generation feature that summarizes fees and costs. | 13 | Medium | 22 | Not Started
12.2 | Create a UI component for financial system agents to generate and view reports. | 5 | Medium | 10 | Not Started
13 | System for Managing Reservations |  |  |  | Not Started
13.1 | Implement a reservation system backend to handle booking logistics. | 8 | High | 15 | Not Started
13.2 | Design a user-friendly interface for managing and viewing reservations. | 5 | High | 10 | Not Started
14 | Reserving Common Facilities |  |  |  | Not Started
14.1 | Develop a calendar-like interface for condo owners/rental users to make reservations. | 8 | High | 14 | Not Started
14.2 | Ensure integration with the reservation system for real-time availability and booking. | 8 | High | 16 | Not Started
15 | Viewing Facility Availabilities |  |  |  | Not Started
15.1 | Create a feature to display real-time availability of common facilities. | 5 | High | 10 | Not Started
16 | First-Come-First-Serve Reservation |  |  |  | Not Started
16.1 | Implement logic to enforce first-come-first-serve booking within the reservation system. | 8 | High | 16 | Not Started

## Agile Project Plan - BLANK
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
Sprint 1
Feature 1
Feature 2
Feature 3
Sprint 2
Feature 4
Feature 5
Feature 6
Sprint 3
Feature 7
Feature 8
Feature 9